## Slide 1: Buyer Segmentation Project Overview
A high-level guide to conducting a buyer segmentation project

## Slide 2: Relevant Terms & Definitions in Buyer Segmentation
TERM | DEFINITION
BUYER PERSONA | A fictional representation of a person in a role within an account. A persona may map directly to a title or range of titles. Personas, when collaborating on a problem, share some common mental and emotional characteristics, though each may experience them differently or at different times.
BUYING TEAM | A group of Personas who share mutual interest in solving a particular problem, but who may not otherwise regularly collaborate. Members of the Buying Team may perceive the problem differently, may have variable sensitivity to its severity or the value of solving the problem, and even have conflicting values, objectives or views. The sales methodology must bring the Buying Team into harmony to the extent possible or risk a no-decision outcome or devolving to the least common denominator solution option.
BUYER’S JOURNEY | A generally linear but often looping path from the point at which buyers recognize a problem they cannot ignore to dimensioning the problem, defining current state and a desirable future state, determining urgency, gathering information on potential approaches to solving the problem, to identifying capabilities required, to mapping to product and service offerings from vendors purporting to solve the problem, to selecting a vendor, to negotiating terms, to implementing a solution.
BUYER STAGE | Discrete and identifiable markers of how buyer’s mental and emotional state changes and how their commitment to solving a problem deepens. Their behavior—what they’re saying or doing--provides evidence about what stage they’re in. Each buyer stage requires solving or satisfying criteria before a buying process will progress. In practice, buyers frequently loop back when they encounter new or conflicting information. Each persona may be in a different buyer stage at any point in time, and buying tends not to happen until personas align.
 | Note: Buyers do not think of themselves as such; nor do they think of vendor offerings as solutions. Buyers think of themselves as problem solvers and vendors as potential enablers. True solutions usually comprise changes in people or process orchestrated or accelerated by the impacts of technological or service capabilities.

## Slide 3: Typical Consulting Timeline for Completing a Buyer Segmentation Project
IMPLEMENTATION
 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
1 | Assemble project team and determine strategic objectives that the buyer segmentation initiative aligns with; are you entering new markets, new products, new verticals? |  |  |  |  |  | 
2 | Identify personas and develop interview question bank |  |  |  |  |  | 
3 | Identify customer & 3rd party interviews across Buying Team |  |  |  |  |  | 
4 | Confirm buyers’ journey stages and persona sections to build |  |  |  |  |  | 
5 | Conduct customer & 3rd party interviews |  |  |  |  |  | 
6 | Interview field members (sales and field marketing reps) & leadership across all geos/industries |  |  |  |  |  | 
7 | Document and analyze common themes |  |  |  |  |  | 
8 | Validate findings during cross-functional working groups |  |  |  |  |  | 
9 | Develop initial generic buyers’ journey |  |  |  |  |  | 
10 | Create and design persona format |  |  |  |  |  | 
11 | Develop persona journey and BT dynamics; document v1 and review with working groups |  |  |  |  |  | 
12 | Roll out management communication plan, develop training and coaching plans |  |  |  |  |  | 
13 | Launch buyer segmentation training and coaching |  |  |  |  |  | 
14 | Use journeys and personas to develop content (Marketing) and design sales tactics (Sales) |  |  |  |  |  | 
15 | Develop ongoing episodic data gathering-- directly from customers, sales, partners, customer success. Update journeys, personas and Buying Team patterns periodically according to dynamism of your market. |  |  |  |  |  | 
*Adjust timeline in view of your company’s maturity, breadth, portfolio complexity, customer base and available personnel resources
PRE-KICKOFF
EXECUTION

## Slide 4: Pitfalls & Best Practices to Consider When Conducting a Buyer Segmentation Exercise
STAGE/PHASE | PITFALLS | BEST PRACTICES
PRE-KICKOFF | Insufficient executive buy-in Waiting too long to schedule persona interviews Failure to set expectations of executives’ role in roll-out and driving early usage of new tools | Set expectation of 5-6 persona interviews per persona Sales team recruited to infuse ‘by sales for sales’ feel Executive sponsor involved in pilot and training of buyer segmentation
PROTOTYPE | Key personas are not validated by executives and sales Not enough personas to capture full buying team Persona interviews that provide little or no insight Small sample sizes treated as conclusive | Begin with pivotal personas. Too many personas can overwhelm a sales and marketing org Deepen questions as multiple interviews validate initial questions Require 3 repeats of theme before including in personas
WORKING PROTOTYPE | Lacking prescription on how to implement the deliverables Coaching is a check the box activity Getting the wrong people on the pilot team | Be explicit in the individuals you request to be on the pilot team Core team owns coaching early in the pilot, and shadows transitioning to sales managers Pilot results are tracked and measured
TRAINING | Trainers not comfortable delivering the material Too much theory, not enough experiential learning Lack of prescriptiveness for how sellers use the tools | Conduct Train the trainer, with prework and post training follow up Promote quick wins and best practices from pilot Include exercises that use each tool
COACHING | No accountability around adopting the tools Coaches cannot effectively coach to the topics | Provide coaching cadence and assistance after training Have execs model the usage of tools continuously Shadow Sales Managers and ensure they can coach their teams Ensure coaching is measurable, both in coaching activities (1 on 1s, ride along) and in results (improved win rate, pipeline build etc.)

## Slide 5: Typical Resources & Team to Complete Buyer Segmentation Initiative
ROLE ON BUYER SEGMENTATION EFFORT | EXECUTIVE SPONSOR(S) | DAY-TO-DAY LEADER | SALES EVANGELISTS | SUPPORTING MEMBERS
PRIMARY RESPONSIBILITIES | Set objectives and success metrics Communicate value and expectations Model application of concepts, terms and tools Drive organizational change management | Oversee the completion of the exercise Ensure business context is included into work product Deliver quick wins to functional leaders to demonstrate value | Provide field-level input Participate in pilots Witness to broader organization | Orchestrate the interviews Build training materials Craft the coaching processes Shadow the coaching process Model behaviors
LEVEL OF INVOLVEMENT IN EFFORT | Periodic Updates & Decisions | Regular guidance according to project pace | Limited, few, specific occasions | Variable by role; specific, targeted, timely
COMMON ROLE IN A COMMERCIAL TEAM | Head of Sales and top lieutenants | Marketing and/or Sales Enablement leader | Influential SDRs, sellers and 2-3 first line managers | Marketing team Sales managers, directors, VPs

## Slide 6
Schedule a session with your advisor
SBI Advisors help clients with practical advice, whether strategic or surgically tactical, to drive revenue and growth.
Contact your advisor to schedule a work session and tune this guidance to your situation.
Login to SBI Pro:
https://pro.sbigrowth.com/
For more resources like this, contact your advisor or visit SBI Pro.