## Sheet1
Sample Communications Plan for a Sales Compensation Plan change (assumes some Marketing roles also impacted.)
Task # | Item | Start Date | Audience | Frequency | From | Owner
1 | Implement internal info portal on website | November 1st | Sales & Marketing | Ongoing | - | Sales Ops
2 | Initial broadcast email to ALL | November 1st | All | One time | CSO + CHRO | Sales Ops
3 | Initial email to Sales & Marketing - Theme announced | November 2nd | Sales & Marketing | One time | CSO + CMO | Mktg Ops
4 | Thank you email to initial comp project expert panels | November 5th | Specific individuals + managers | One Time | CSO + CMO | Sales Ops
5 | Newsletter (by email) Story 1: Need for comp change | November 9th | Sales & Marketing | One Time | CSO | Sales Ops
6 | Blog on portal regarding new comp plan - from Rep perspective | November 15th | Sales Reps | One Time | Top Reps | Sales Ops
7 | Instructional email to SMs - team meeting talk tracks | November 16th | Sales Managers | One Time | VP Sales Ops | Sales Ops
8 | Newsletter Story 2: Comp change timeline | November 23rd | Sales & Marketing | One Time | VP Sales Ops | Sales Ops
9 | Virtual town hall with SMs - explain + Q&A | November 26th | Sales Managers | One Time | CSO | Sales Ops
10 | SMs hold team meetings to explain and answer why questions | November 27th | SM & Reps | One Time | SMs | Sales Ops
11 | Newsletter Story 3: Change Management curve | November 30th | Sales & Marketing | One time | VP Sales Ops | Sales Ops
12 | Release explanation video - email announcement | December 3rd | Sales & Marketing | One Time | VP Sales Ops | Sales Ops
13 | Newsletter Story 4: Sample paychecks (old and new) | December 5th | Sales & Marketing | One Time | VP Sales Ops | Sales Ops
14 | Letter to Strategic Customers | December 7th | Strategic Customers | One Time | CSO + CMO | Mktg Ops
15 | Newsletter Story 5: Expected behaviors from new comp plan | December 12th | Sales & Marketing | One Time | CSO | Sales Ops
16 | Email reminder about rollout start date | December 13th | Sales & Marketing | One Time | VP Sales Ops | Sales Ops
17 | SMs hold team meetings to discuss reporting changes | December 14th | SM & Reps | One Time | SMs | Sales Ops
18 | New Rep dashboard Training | December 17th | Sales Reps | One time | VP Sales Ops | Sales Ops
19 | Email to announce official rollout | December 31st | All | One Time | CSO | Sales Ops
20 | Newsletter Stories: On rollout progress and quick wins | January 3rd | Sales & Marketing | Monthly | VP Sales Ops | Sales Ops
21 | Progress report with statistics | April 5th | Sales & Marketing | One time | VP Sales Ops | Sales Ops