## Summary & Instructions
Tab Overview
Content | Total number of content to develop for suggested plays
Total Content Analysis | Analysis for time to develop all content
Q1 | Analysis for Q1 content development. Includes (1) prioritization of content, verticals, and personas, (2) total number of content to be developed, (3) estimated effort to develop. (ILLUSTRATIVE)
Q2 | Analysis for Q2 content development. Includes (1) prioritization of content, verticals, and personas, (2) total number of content to be developed, (3) estimated effort to develop. (ILLUSTRATIVE)
Timeline for Content Dev | Illustrative timeline of how ACME would prioritize its content development, starting with SBI suggested prioritization for Q1 2022 and measurement criteria for determining Q2 approach (ILLUSTRATIVE)
Types of Cells
Assumption | Cell can be edited
Formula | Do not edit cell
Create new in Q1 | In Content Tab | (ILLUSTRATIVE)
Create new in Q2 | In Content Tab | (ILLUSTRATIVE)
Glossary
Content
Pillar Content | The primary piece of content that will attract the target vertical and persona, such as whitepapers, competitive analysis, etc. Pillar content will be used across plays. For example, a competitive comparison is created for Play 2 (Create Sway), but it can be used for advertisement material in Play 1a & 1b (Air Cover) and can be included as a part of the ‘Champion Packet’ in Play 3 (Champion Content)
Satellite Content | Content meant to advertise and distribute pillar content. For example, a display ad that links to a whitepaper on the ACME website.
Sales Template | Content that is used within the sales process and has portions that will updated specifically to the target account. This can be a way to share multiple pieces of pillar content. For example, a deal brochure will have key customer challenges, proposed solution, work completed/discussions had, and proposed benefit/lift/ROI. The template would only contain stylized sections, without actual text; text to be filled in by the owner of the deal.
Email Template | A campaign email template for your marketing automation platform or a drafted email template used that can be used by the sales team to expedite common touchpoints (i.e., a follow up email after a demo).

## Content
|  |  | Vertical A |  |  |  |  | Vertical B |  |  |  |  | Vertical C |  |  |  |  | Vertical D
Type | Content (Illustrative) | Owner | Ops | Proc | CMO | Risk | CFO | Ops | Proc | CMO | Risk | CFO | Ops | Proc | CMO | Risk | CFO | Ops | Proc | CMO | Risk | CFO
Pillar | ‘Do Nothing’ Risks | Growth Marketing Manager | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | Y | N | N | N | N
Satellite | Facebook Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | LinkedIn Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Google SEM Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Content Syndication | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Banner Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Solution Capabilities | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Facebook Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | LinkedIn Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Google SEM Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Content Syndication | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Satellite | Banner Ad | Content Developer | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Competitive Analysis | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Why [Solution] Matters | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Educational Content | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | [Solution Area] Readiness Assessment | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Requirements for Successful Rollout | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Benefits for Contactors | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Pillar | Benefits by Persona | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Sales Template | Deal Brochure Template | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Sales Template | Alignment Document (i.e., Close Plan) Template | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Email Template | Digital Ad Campaign Email Template | Growth Marketing Manager | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Email Template | Digital Ad Campaign Email Template (Strategic Accounts) | Sales Executive | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Email Template | 'Create Sway' Email Template; to send personalized note with sway content attached | Sales Executive | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Email Template | 'Champion Packet' Email Template; to share the champion packet and explain its content, benefits, and uses | Sales Executive | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
Email Template | 'Champion Packet' Email Template; to share the champion packet and explain its content, benefits, and uses | Sales Executive | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
|  | TOTAL | 520
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is ILLUSTRATIVE to a pillar content and satellite content approach. SBI does not suggest going with the 'Do Nothing' Risk as a first campaign.

## Total Content Analysis
Total Content to Be Developed
Type | General | Customized to Vertical | Customized to Persona
Type of content that needs to be developed | 80% of effort to develop the content | 10% of effort to develop the content - customizing parts of the general content to be specific to the vertical | Final 10% of effort to develop the content- customizing to a persona within that vertical
Pillar | 9 | 36 | 180
Satellite | 10 | 40 | 200
Sales Template | 2 | 8 | 40
Email Template | 5 | 20 | 100
Total |  |  | 520
Estimated Effort
Type | General | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | Customized to Vertical | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | Customized to Persona | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs)
Pillar | 9 | 40 | 360 | 36 | 2 | 72 | 180 | 2 | 360
Satellite | 10 | 8 | 80 | 40 | 1 | 40 | 200 | 1 | 200
Sales Template | 2 | 4 | 8 | 8 | 1 | 8 | 40 | 1 | 40 | Total Time To Develop Content
Email Template | 5 | 4 | 20 | 20 | 0.5 | 10 | 100 | 0.5 | 50 | Hrs | Dys
Total |  |  | 468 |  |  | 130 |  |  | 650 | 1248 | 156
Estimated Effort by Role | [6 empty] | Notes
|  | % Ownership of Deliverable | # of Content to Create | # of Content to Customize (Vertical) | # of Content to Customize (Persona) | Total Estimated Effort (hrs)
Content Writer (i.e., owner of pillar content, hunting down and meeting with Content SMEs to get relevant information, clearly and concisely) | [5 empty] | 440.62
| Pillar | 60% | 10 | 8 | 80 | 387.6
| Satellite | 10% | 2 | 4 | 8 | 3.22
| Sales Template | 60% | 5 | 4 | 20 | 49.8
| Email Template | 70% | 0 | 0 | 468 | 0
Content SME (i.e., the main contributor on pillar content, providing details on product/vertical/persona, can be a Sales Executive, a Growth Marketing Manager, a Product Marketing Manager) | [5 empty] | 173.95
| Pillar | 25% | 10 | 8 | 80 | 161.5
| Satellite | 0% | 2 | 4 | 8 | 0
| Sales Template | 15% | 5 | 4 | 20 | 12.45
| Email Template | 15% | 0 | 0 | 468 | 0
Content Developer (i.e., develops satellite content, owns the final step of making all types of content digestible and visually appealing) | [5 empty] | 134.18
| Pillar | 15% | 10 | 8 | 80 | 96.9
| Satellite | 90% | 2 | 4 | 8 | 28.98
| Sales Template | 10% | 5 | 4 | 20 | 8.3
| Email Template | 10% | 0 | 0 | 468 | 0
Sales Exec (i.e., can be SME, owns development for any content specific to their assigned strategic accounts) | [5 empty] | 0
| Pillar |  | 10 | 8 | 80 | 0
| Satellite |  | 2 | 4 | 8 | 0
| Sales Template |  | 5 | 4 | 20 | 0
| Email Template |  | 0 | 0 | 468 | 0
SDR (i.e., can be SME) | [5 empty] | 0
| Pillar |  | 10 | 8 | 80 | 0
| Satellite |  | 2 | 4 | 8 | 0
| Sales Template |  | 5 | 4 | 20 | 0
| Email Template |  | 0 | 0 | 468 | 0
Total Capacity by Role
| Resource Assumption (FTE or Contractor) | Number of Hours in Time Period (i.e., 168 hours a in the month of January) | Available Hours | Required Hours to Develop Recommended Content | Gap (hrs)
Content Writer | 80% | 168 | 134.4 | 440.62 | -306.22
Content SME | 15% | 168 | 25.2 | 173.95 | -148.75
Content Developer | 50% | 168 | 84 | 134.18 | -50.18
Sales Exec | 0.25 | 44 | 0 | 44
SDR | 0.9 | 158.4 | 0 | 158.4
Total |  | 706.4 | 243.6 | 951.15
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What % of the resource's time can be spent on content development.

## Timeline for Content Dev
Q1 |  |  |  | MEASURE & ANALYZE Before Q2, determine if focus will be on.. (1) Expanding pillar content to new verticals and/or personas. Choose this option if interactions, conversion rates, and wins are not improving within the verticals. OR (2) Creating new pillar content for prioritized verticals and personas. Choose this option if seeing increased interactions, higher conversion rates, and wins within the verticals. | Q2
General Content | Vertical | Persona | Total # of Content |  | General Content | Vertical | Persona | Total # of Content
Pillar - Prioritize 3 types of pillar content | Customize for 2 verticals | Customize for 2 personas within the verticals | 12 |  | Pillar - Create 3 types of new pillar content | Customize for 2 verticals (Upstream and Midstream Oil & Gas) | Customize for 2 personas within the verticals | 12
Satellite - Develop 5 types of satellite content to advertise pillar content. Choose one pillar content for first 8 week ad campaign. Analyze success and determine if new pillar content should be used for second 8-week campaign. | Customize for 2 verticals | Customize for 2 personas within the verticals | 20 |  | Satellite - If prior campaigns have been successful; use same pillar content and develop no new satellite content. Will only customize existing content to target new persona. | N/A (already developed in Q1) | Customize for 1 personas within the verticals | 5 (customized only)
Sales Template - Develop the 2 sales templates suggested for Play 4 | Customize for 2 verticals | Customize for 2 personas within the verticals | 8 |  | Sales Template - Customize existing to new persona | N/A (already developed in Q1) | Customize for 1 personas within the verticals | 2 (customized only)
Email Template - Develop the 2 of the email templates suggested | Customize for 2 verticals | Customize for 2 personas within the verticals | 8 |  | Email Template - Customize existing to new persona | N/A (already developed in Q1) | Customize for 1 personas within the verticals | 2 (customized only)

## Q1
Prioritization for Q1
| # to focus on in Q1 | Reason
Pillar Content | 3 | Pillar content chosen should be most valuable and likely already existing but needs a refresh. SBI suggests 'Do Nothing Risks', 'Competitive Analysis' and 'Solution Capabilities'
Satellite Content | 5 | Develop 5 types of satellite content to advertise pillar content (Play 1a & 1b). Choose one pillar content (i.e., 'Do Nothing Risks') for first 8 week ad campaign. Analyze success and determine if new pillar content should be used for second 8-week campaign
Sales Template | 2 | Develop the 2 sales templates suggested for Play 4
Email Template | 2 | Develop the 2 of the email templates suggested (Play 1a & 1b - Digital Ad Campaign Emails)
Verticals | 2 | SBI recommends choosing verticals aligned with strategic accounts for Q1.
Personas | 2 | Prioritize 2 personas that are most commonly sold to.
Content to Be Developed in Q1
| General | Customized to Vertical | Customized to Persona
Type of content that needs to be developed | 80% of effort to develop the content | 10% of effort to develop the content - customizing parts of the general content to be specific to the vertical | Final 10% of effort to develop the content- customizing to a persona within that vertical
Pillar | 3 | 6 | 12
Satellite | 5 | 10 | 20
Sales Template | 2 | 4 | 8
Email Template | 2 | 4 | 8
Total |  |  | 48
Estimated Effort
| General |  |  | Vertical |  |  | Persona
Type | # of General Content to be Developed | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | # of Content to be Customized to a Vertical | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | # of Content to be Customized to a Persona | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs)
Pillar | 3 | 40 | 120 | 6 | 2 | 12 | 12 | 2 | 24
Satellite | 5 | 4 | 20 | 10 | 1 | 10 | 20 | 1 | 20
Sales Template | 2 | 8 | 16 | 4 | 1 | 4 | 8 | 1 | 8 | Total Time To Develop Content
Email Template | 2 | 1 | 8 | 4 | 1 | 4 | 8 | 1 | 8 | Hrs | Dys
Total |  |  | 164 |  |  | 30 |  |  | 60 | 254 | 31.75
Estimated Effort by Role | [6 empty] | Notes
|  | % Ownership of Deliverable | # of Content to Create | # of Content to Customize (Vertical) | # of Content to Customize (Persona) | Total Estimated Effort (hrs)
Content Writer (i.e., owner of pillar content, hunting down and meeting with Content SMEs to get relevant information, clearly and concisely) | [5 empty] | 125.2
| Pillar | 60% | 3 | 6 | 12 | 93.6
| Satellite | 10% | 5 | 10 | 20 | 5
| Sales Template | 60% | 2 | 4 | 8 | 16.8
| Email Template | 70% | 2 | 4 | 8 | 9.8
Content SME (i.e., the main contributor on pillar content, providing details on product/vertical/persona, can be a Sales Executive, a Growth Marketing Manager, a Product Marketing Manager) | [5 empty] | 45.3
| Pillar | 25% | 3 | 6 | 12 | 39
| Satellite | 0% | 5 | 10 | 20 | 0
| Sales Template | 15% | 2 | 4 | 8 | 4.2
| Email Template | 15% | 2 | 4 | 8 | 2.1
Content Developer (i.e., develops satellite content, owns the final step of making all types of content digestible and visually appealing) | [5 empty] | 72.6
| Pillar | 15% | 3 | 6 | 12 | 23.4
| Satellite | 90% | 5 | 10 | 20 | 45
| Sales Template | 10% | 2 | 4 | 8 | 2.8
| Email Template | 10% | 2 | 4 | 8 | 1.4
Sales Exec (i.e., can be SME, owns development for any content specific to their assigned strategic accounts) | [5 empty] | 0
| Pillar |  | 3 | 6 | 12 | 0
| Satellite |  | 5 | 10 | 20 | 0
| Sales Template |  | 2 | 4 | 8 | 0
| Email Template |  | 2 | 4 | 8 | 0
SDR (i.e., can be SME) | [5 empty] | 0
| Pillar |  | 3 | 6 | 12 | 0
| Satellite |  | 5 | 10 | 20 | 0
| Sales Template |  | 2 | 4 | 8 | 0
| Email Template |  | 2 | 4 | 8 | 0
Total Capacity by Role
| Resource Assumption (FTE or Contractor) | Number of Hours in Time Period (i.e., 168 hours a in the month of January) | Available Hours | Required Hours to Develop Recommended Content | Gap (hrs)
Content Writer | 80% | 168 | 134.4 | 125.2 | 9.2
Content SME | 15% | 168 | 25.2 | 45.3 | -20.1
Content Developer | 50% | 168 | 84 | 72.6 | 11.4
Sales Exec | 0.25 | 44 | 0 | 44
SDR | 0.9 | 158.4 | 0 | 158.4
Total |  | 706.4 | 243.6 | 445.5
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What % of the resource's time can be spent on content development.

## Q2
Prioritization for Q2
| # to focus on in Q1 | Reason
Pillar Content | 3 | New pillar content should be developed for either the same industries if there's been initial success or new ones if expansion is required.
Satellite Content | 0 | 'Do Nothing' campaign has shown success; expand to new persona (CFO)
Sales Template | 0 | Templates already created, customize them for a new persona (CFO)
Email Template | 0 | Templates already created, customize them for a new personas (CFO)
Verticals | 2 | Same verticals to continue success
Personas | 2 | Same personas to continue success; expand to CFO if bandwidth allows
Content to Be Developed in Q2
| General | Customized to Vertical | Customized to Persona
Type of content that needs to be developed | 80% of effort to develop the content | 10% of effort to develop the content - customizing parts of the general content to be specific to the vertical | Final 10% of effort to develop the content- customizing to a persona within that vertical
Pillar | 3 | 6 | 12
Satellite | 0 | 0 | 5
Sales Template | 0 | 0 | 2
Email Template | 0 | 0 | 2
Total |  |  | 21
Estimated Effort
| General |  |  | Vertical |  |  | Persona
Type | # of General Content to be Developed | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | # of Content to be Customized to a Vertical | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs) | # of Content to be Customized to a Persona | Estimated Effort per One Piece of Content (hrs) | Total Estimated Effort (hrs)
Pillar | 3 | 70 | 210 | 6 | 4 | 24 | 12 | 2 | 24
Satellite | 0 | 4 | 0 | 0 | 1 | 0 | 5 | 1 | 5
Sales Template | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 1 | 2
Email Template | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 1 | 2 | Total Hours | Total Days
Total |  |  | 210 |  |  | 24 |  |  | 33 | 267 | 33.375
Estimated Effort by Role | [6 empty] | Notes
|  | % Ownership of Deliverable | # of Content to Create | # of Content to Customize (Vertical) | # of Content to Customize (Persona) | Total Estimated Effort (hrs)
Content Writer (i.e., owner of pillar content, hunting down and meeting with Content SMEs to get relevant information, clearly and concisely) | [5 empty] | 157.9
| Pillar | 60% | 3 | 6 | 12 | 154.8
| Satellite | 10% | 0 | 0 | 5 | 0.5
| Sales Template | 60% | 0 | 0 | 2 | 1.2
| Email Template | 70% | 0 | 0 | 2 | 1.4
Content SME (i.e., the main contributor on pillar content, providing details on product/vertical/persona, can be a Sales Executive, a Growth Marketing Manager, a Product Marketing Manager) | [5 empty] | 65.1
| Pillar | 25% | 3 | 6 | 12 | 64.5
| Satellite | 0% | 0 | 0 | 5 | 0
| Sales Template | 15% | 0 | 0 | 2 | 0.3
| Email Template | 15% | 0 | 0 | 2 | 0.3
Content Developer (i.e., develops satellite content, owns the final step of making all types of content digestible and visually appealing) | [5 empty] | 43.6
| Pillar | 15% | 3 | 6 | 12 | 38.7
| Satellite | 90% | 0 | 0 | 5 | 4.5
| Sales Template | 10% | 0 | 0 | 2 | 0.2
| Email Template | 10% | 0 | 0 | 2 | 0.2
Sales Exec (i.e., can be SME, owns development for any content specific to their assigned strategic accounts) | [5 empty] | 0
| Pillar |  | 3 | 6 | 12 | 0
| Satellite |  | 0 | 0 | 5 | 0
| Sales Template |  | 0 | 0 | 2 | 0
| Email Template |  | 0 | 0 | 2 | 0
SDR (i.e., can be SME) | [5 empty] | 0
| Pillar |  | 3 | 6 | 12 | 0
| Satellite |  | 0 | 0 | 5 | 0
| Sales Template |  | 0 | 0 | 2 | 0
| Email Template |  | 0 | 0 | 2 | 0
Total Capacity by Role
| Resource Assumption (FTE or Contractor) | Number of Hours in Time Period (i.e., 168 hours a in the month of January) | Available Hours | Required Hours to Develop Recommended Content | Gap (hrs)
Content Writer | 80% | 168 | 134.4 | 157.9 | -23.5
Content SME | 15% | 168 | 25.2 | 65.1 | -39.9
Content Developer | 50% | 168 | 84 | 43.6 | 40.4
Sales Exec | 0.25 | 44 | 0 | 44
SDR | 0.9 | 158.4 | 0 | 158.4
Total |  | 706.4 | 243.6 | 469