## Slide 1: Change Management and Communication Planning
A guide to execute successful GTM launches

## Slide 2: A successful GTM launch depends on tightly structured and managed communications and change management
Objectives
Ensures all levels of the GTM organization understand the FYXX strategy and “what’s in it for them”
Support management of GTM changes through pre-launch, launch and post-launch
Leverage the 4 stages of change management to influence the design and delivery of communications
3 Communication Plan Components
Calendar
Covers key GTM pre-launch, launch and post launch communication activities
Organized around cascading messages
Connects Regions with other Functions
Completion Tracker
Tracks content completeness for each key communication activity
Communication Briefs
For key communication activities on the Calendar, essential comm elements are outlined and messaging drafted
Reinforces logical cascading of messaging with careful consideration of what gets communicated to who

## Slide 3: Use the four stages of change management to inform the FYXX GTM plan
Stage 1 | Stage 2 | Stage 3 | Stage 4
Shock, Rejection | Anger, Fear | Initial Acceptance | Commitment
Communicate Clearly & Often | Listen & Observe | Offer Training & Opportunities | Celebrate Success
Impact
DENIAL
OBJECTION
EXPLORATION
ADOPTION
With any transition, the organization must manage through the change. This includes allowing people to progress through the behavior stages after the initial impact.
Risks to success are real. Watch for specific negative reactions.
Take specific actions to help them manage through the change and eventually celebrate success.
Behavior
Actions

## Slide 4: A Communications Strategy and Framework should be used to ensure messaging reaches the right audience at the right time
Communications Strategy Framework
WHY are we
communicating?
HOW is the message being communicated?
HOW is the message being communicated?
WHO is being
communicated to?
WHAT needs to be communicated?
WHEN is the communication being delivered and how often?
Desired
Outcomes
Method of
Delivery
Communicator
Audience
Message
Timing &
Frequency

## Slide 5: While specific comms activities fall into the 4 stages of change management, expect a mixture of responses from employees
Alignment to Change Mgmt Plan: | All change management and communication plan activities will be tied to the 4 stages of the change management framework. This will ensure activities are impactful and help AVP / reps hit the ground running after change is implemented.
Change Management Framework
 | Communicate Clearly & Often | Listen & Observe | Offer Training Opportunities | Celebrate Success
Pre-Launch | CRO Kickoff Geo/Industry/Global Kickoff CRO Roadshow Leadership Session SKO Meeting | Weekly meetings with Regions / Global leaders 1 on 1 meetings between EVP and VPs Breakout sessions at SKO | Change Management Training for Managers Comp Plan training for Managers | Message from CRO kicking off change
Launch | Messaging to: Front line Managers Front Line Staff Customers Partners | Office Hours to monitor and address specific concern (Comp Plans, etc.) | Comp Plan Training for quota bearing staff | Message from CRO announcing change
Post-Launch | Weekly/Monthly updates on Transformation Workstreams Monthly / quarterly updates on performance | Employee “Pulse” surveys Daily Team Scrums 1 on 1 Manager / Employee Meetings Customer Surveys / NPS Partner Surveys | Sales Manager Training Sales Enablement Training Detailed Roles & Responsibilities Training Other trainings (TBD) | KPI / Metrics dashboards Celebrate big win Recognize individual, team and company achievements Document and socialize employee stories which promote the new way of working
Action Items
Establish “global communication calendar” that is be updated with input from each regional core team
Socialize comms with regions prior to implementing
Develop content for key messaging events, surveys, training modules, etc.
Update Comms plan dates, as needed

## Slide 6: Managing comms details will ensure a successful launch; a manager / staff communication tracker will support this effort
Examples:
Managers should receive communication to by XX date
Exit notifications can start by XX date and need to be completed by XX date
Front line staff communications can start XX date and need to be completed by XX date
Template can be used to track the communication between Managers, Front Line Staff and Exiting Employees during critical launch period (example follows)
Headcount data is requested to fill-in template; completion by XX date will promote successful comms tracking during Launch
Completed manager/staff communications will be indicated on the template
The communication plans are consolidated into a master project plan so they can be compared and used for tracking during GTM launch week
Milestones are created for each day to use in tracking GTM launch progress
The GTM Command Center uses the master project plan to track daily progress and ensure a smooth rollout
Communication Guidelines
Managers
Staff
Exits
EMEA
AMS
APJ
M Tu W Th Fr
Provide Communication
Guidelines
Complete Launch Week
Mgr/Staff Comms Tracker
Consolidate Regional
Communication plans
Track Communication progress during GTM Launch Week

## Slide 7: Month, Year Communication and Change Management Activities
Month |  |  |  | 
Monday | Tuesday | Wednesday | Thursday | Friday
 |  | 1 | 2 | 3
6 | 7 | 8 | 9 | 10
13 | 14 | 15 | 16 | 17
20 | 21 | 23 | 23 | 24
27 Holiday | 28 | 29 | 30 | 31
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
Comms and Communication Workstream Kickoff
Complete V1 Comms and Communication Workstream
Global Product Kickoff
Global Operation Leaders
GTM Leadership Roadshow: Partners
GTM Leadership Roadshow: APJ
GTM Leadership Roadshow: EMEA
GTM Leadership Roadshow: AMS
GTM Leadership Roadshow : Global Product
Complete V2 Comms and Communication Workstream
Share V2 Comms and Communication Plan with Regions (Weekly)
Final IT Testing and Validation
Region EVPs to communicate Geo/Industry leaders of GTM launch date change
Example

## Slide 8: Week of Day, Month, Year Communication and Change Management Activities
 | Month |  |  |  |  |  | 
 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
CRO / Leadership & Org | 3 Holiday | 4 | 5 | 6 | 7 | 8 | 9
Talent |  |  |  |  |  |  | 
Comp & Quota |  |  |  |  |  |  | 
IT |  |  |  |  |  |  | 
Partner Comms Review
Global Ops Comms Plan Review
GTM Leadership Roadshow: CS
GTM Leadership Roadshow: Ops
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
Quota assignments by each Region
Step 1
Step 2
Step 3
Provide quota guidelines to Regions
Region Financial data review
User communication of CRM outage
Reminder communication of CRM outage
Example

## Slide 9: Week of Day, Month, Year Communication and Change Management Activities
 | Month |  |  |  |  |  | 
 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
CRO / Leadership & Org | 10 | 11 | 12 | 13 | 14 | 15 | 16
Talent |  |  |  |  |  |  | 
Comp & Quota |  |  |  |  |  |  | 
IT |  |  |  |  |  |  | 
GTM Leadership KO – Day 2
Managers Notified of Impacted Staff
Comms Plan document review
User communication of tech platform outage
Reminder communication of tech platform outage
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
CRO FY23 Kick-off Email
GTM Leadership KO – Day 1
Global Function Planning Workshops
8 events for the 3 Regions
Region leaders communicate GTM Structure and Planned Changes
(1:1 meetings to walk through rationale)
Quota assignments by each Region (cont.)
Example

## Slide 10: Week of Day, Month, Year Communication and Change Management Activities
 | Month |  |  |  |  |  | 
 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
CRO / Leadership & Org | 17 | 18 | 19 | 20 | 21 | 23 | 23
Talent |  |  |  |  |  |  | 
Comp & Quota |  |  |  |  |  |  | 
IT |  |  |  |  |  |  | 
CRO Quota final Sign off
CRM Ends
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
GTM launch msg from CRO
Sales Kickoff – Day 1
Global Function Planning Workshops
3 events for the 3 Regions
SKO F/U Email, Survey, & GTM Website Launch
CRM outage period
CRM UAT Starts
QMT file review
Quota assignment review
Comp Plan Training for Managers
Total of 2 time slots per region for 6 meetings
Separation Agreements for affected employees finalized
Change Management Training for Managers with Affected Teams
Managers will be paired with HR partner
Sales Kickoff –
Day 2
Sales Kickoff –
Day 3
Example

## Slide 11: Week of Day, Month, Year Communication and Change Management Activities
 | Month |  |  |  |  |  | 
 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
CRO / Leadership & Org | 24 | 25 | 26 | 27 | 28 | 29 | 30
Talent |  |  |  |  |  |  | 
Comp & Quota |  |  |  |  |  |  | 
IT |  |  |  |  |  |  | 
EVP Launch Message to Region
Managers communicate comp and assignments via 1:1 sessions
Geo VP messaging to Teams
Start Messaging to Partners
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
Start Messaging to Customers
Office Hours
All Geo & Functional leaders host all-hands meeting to reinforce manager messaging
Manager messaging to teams
Managers + HR notify impacted employees
Managers notify staff of impacted employees
Managers email details to employees after 1:1 conversation
Comp Plan Training for Quota bearing staff
Total of 2 time slots per region for 6 meetings
Example

## Slide 12: Month, Year Communication and Change Management Activities
Month |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
30 | 31 | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 23 | 23 | 24 | 25 | 26
27 | 28 |  |  |  |  | 
Other recommended communications events to be scheduled by Region / Geo / Field / Team managers
Daily Scrums
Manager - Staff 1 on 1 meetings
Monthly Region / Geo “all hands” meetings
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
Quota comms to reps starts
IT Comms / Activities
tech platform UAT Starts
Office Hours
GTM Leader Roadshows for GTM staff
GTM staff Bi-Weekly Survey
Begin Daily Scrums
Begin 1 on 1 meetings
Geo “All Hands” Meeting
Transformation Workstream Monthly Update
Monthly Customer Survey
Monthly Partner Survey
Begin Roles and Responsibilities Training
GTM staff Bi-Weekly Survey
tech platform Upload Code to Production
Global Quota Approval
Quotas comms to mgrs starts
tech platform Agreements Released
Quota acceptance deadline for AEs
Example

## Slide 13: Month, Year Communication and Change Management Activities
Month |  |  |  | 
Monday | Tuesday | Wednesday | Thursday | Friday
 | 1 | 2 | 3 | 4
7 | 8 | 9 | 10 | 11
14 | 15 | 16 | 17 | 18
21 | 23 | 23 | 24 | 25
28 | 29 | 30 | 31 | 
Pre-Launch Activities
Launch Activities
Post-Launch Activities
Completed Activities
GTM staff Bi-Weekly Survey
Geo “All Hands” Meeting
Transformation Workstream Monthly Update (Exact date TBD)
Monthly Customer Survey
Monthly Partner Survey
GTM staff Bi-Weekly Survey
Quarterly GTM staff Survey
Other recommended communications events to be scheduled by Region / Geo / Field / Team managers
Daily Scrums
Manager - Staff 1 on 1 meetings
Monthly Region / Geo “all hands” meetings
Example

## Slide 14: By executing on a cascading communications approach, all GTM changes are accurately communicated in the defined cadence
Cascading messaging throughout the GTM Org
CRO |  | 
FY23 Kickoff to all GTM staff (Pre-SKO) | XX Date | ✔
Post-SKO email | XX Date | ✔
Region EVP |  | 
FY23 Org Announcements to all GTM staff | XX Date | ✔
Geo VP / Industry VP |  | 
FY23 Org Announcements to Geos / Industry | XX Date | Leaders communicate new org design to own team
All Hands Meetings | XX Date | Address the GTM structure & changes
Roles & Resp / New Way of Working Sessions | XX Date | Overview of new R&Rs and team interlocks
Front Line Managers & Staff |  | 
Comp Plan training for Managers | XX Date | ✔
Impacted Staff Notification | XX Date | ✔
Manager / Employee 1 on 1’s | XX Date | ✔
Manager / Team Meeting on Org Changes | XX Date | ✔
Comp Plan Training for Sellers | XX Date | ✔
Office Hours Sessions | XX Date | Scheduled time for Front line Mgs and staff to ask questions related to compensation

## Slide 15: Change Management & Communication Cadence Details
# | Content to be Developed | Description | Due Date | Status | Audience | Content Developer | Delivered By
1 | GTM Leadership Roadshow | Present GTM strategy to Global Cloud Core team |  |  | Region & Global Function Core Teams & Geo / Industry / Global Leaders |  | 
2 | Change Mgt & Communication Plan | Initiate effort and assign responsible person |  |  | Steering Co / Region & Global Function Core Teams |  | 
3 | Beginning of Year message from CRO | CRO kicking off the new year with info about SKO, FY23 GTM launch and January focus |  |  | All GTM staff |  | 
4 | Quota Guidelines | Quota guidelines provided to each Region |  |  | Core Region Teams |  | 
5 | Leadership Summit GTM Content | GTM specific content which will be presented during Leadership Offsite |  |  |  |  | 
6 | Separation Packages | Develop packages for affected employees |  |  | Affected Employees |  | 
7 | Global Function meetings with each Region | Global Function Leaders meet with Region Core teams to provide an overview on how the Global function will support each Region |  |  | Region Core team GEO / Industry leaders |  | 
8 | IT Notifications | Develop content for IT messages announcing system changes and implementation updates |  |  | All System Users |  | 
9 | Employee Agreements | Develop agreement package for employees which includes Individual comp plan, account assignments, quota, etc. |  |  | Front Line Managers, Front Line Staff |  | 
10 | SKO GTM Content | GTM specific content which will be presented during SKO |  |  | SKO Attendees |  | 
11 | SKO Meetings | Three-day SKO meetings |  |  | All SKO Attendees |  | 
12 | Post-SKO Survey | Survey to capture feedback from attendees about the SKO |  |  | All SKO Attendees |  | 
13 | Post-SKO GTM Launch Comms | Post-SKO message from CRO announcing the GTM launch |  |  | All GTM Staff |  | 
14 | Manager / Seller 1:1s | Managers communicate GTM changes 1:1 to employees |  |  | All GTM Managers |  | 
15 | FY23 Quota Communication | Managers begin communicating quota plans to teams |  |  | All GTM Reps |  | 
16 | Comp Plan Training | Comp plan training for AEs – total of two time slots per region for six meetings |  |  | All GTM Reps |  | 
17 | Geo / Functional All-Hands | All Geo and Functional leaders to lead all-hands meeting to reinforce manager messaging |  |  | All GTM Reps & Managers |  | 
18 | Partner Messaging | Messaging conveyed to Partners about the FY23 GTM plan |  |  | Partners |  | 
Milestone Missed
Milestone At Risk
On Track

## Slide 16: …Continued
Milestone Missed
Milestone At Risk
On Track
# | Content to be Developed | Description | Due Date | Status | Audience | Content Developer | Delivered By
19 | Customer Messaging | Messaging conveyed to customers impacted by account reassignments |  |  | Affected Customers |  | 
20 | GTM Leader Roadshows | GTM Roadshow meetings for GTM staff |  |  | All GTM Staff |  | 
21 | Post Launch Survey | Survey to capture feedback after the GTM launch |  |  | All GTM Staff |  | 
23 | Daily Scrum Guidance | Guidance on how to run a daily team scrum |  |  | Managers |  | 

## Slide 17: Example Communications Brief: CRO FY23 GTM Kickoff Email
CRO FY23 GTM KICKOFF EMAIL |  |  | 
Objective / Description: Communicate GTM launch. Include strategy of GTM and guiding principles. Describe key changes to expect vs previous year. Message needs to promote renewed energy and an updated approach to the marketplace. Prior Comms Activity: CRO Roadshows for Regions and Global Functions Next Comms Activity: Region All-Hands Meetings, Sales Kickoff Meetings |  |  | 
Audience: All GTM roles | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email/Teams/Blog/Intranet page |  |  | 
Welcome to 20XX
High-level strategy
Upcoming Events
  Happy New Year. Hope everyone is well-rested from their holiday
  We will continue our evolution regarding our Guiding Principles (list)
  We will recalibrate how we follow our GTM guiding principles in our approach to the market
  We will streamline how we work together
  XX-XX Dates: Sales Kickoff
  XX Dates: FYXX Launch / Go live
Until then…
  Until launch, our selling focus will remain the same as previous year

## Slide 18: Example Communications Brief: Comp Plan Training for Managers
COMP PLAN TRAINING FOR MANAGERS |  |  | 
Objective / Description: Communicate comp plan topical info and related learning. Two comms: One for managers and one for non-manager employees. Provide all information and contacts needed (Mgr only) Outline steps to share with employees simply and comprehensively Prior Comms Activity: Sales Kickoff Next Comms Activity: Go Live, 1:1 manager / employee meetings |  |  | 
Audience: GTM Managers | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email with (1) link to online training / reading, (2) link to systems / instructions, (3) FAQs |  |  | 
Overview
Details
Next Steps
  During the SKO you received an overview of our FYXX strategic priorities / guiding principles.
  The FYXX comp plan provide line-of-sight compensation for your actions supporting these principles
  Comp plan details per role.
  Comp grid; pay scenarios.
  Sales scenario calculator (link to).
  (Mgr) Outline/Script of conversation with employee
  Communicate with your team that 1x1 meetings will be scheduled to discuss FYXX comp.
  Prepare FAQs and 3 possible pay scenarios (low-med-hi) for your team
  Send info and schedule 1x1 meetings

## Slide 19: Example Communications Brief: Sales Kickoff Follow-up Message
SALES KICKOFF FOLLOW-UP COMMUNICATION |  |  | 
Objective / Description: Reinforce messaging from SKO. Drive GTM community by outlining 3 key next steps. Provide links to relevant intranet site(s) including GTM Sales Kickoff replays, main GTM intranet site Prior Comms Activity: Sales Kickoff Next Comms Activity: Go Live |  |  | 
Audience: GTM Community | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email, GTM website |  |  | 
Core FYXX Kickoff Messaging
Next Steps
Reference Material
  Thank you for your focus at the FYXX Sales Kickoff; use our new GTM intranet website.
  We will continue our evolution regarding our Guiding Principles (list)
  Bookmark links to GTM intranet website.
  Familiarize yourself with [Company] and GTM FYXX strategy details.
  Attend any missed SKO sessions and breakouts of pertinent to your role.
  (Managers) Discuss next steps with your team; share relevant content per area/role.
  Prepare for XX Date Go Live; announce Office Hours for any questions/escalations begin XX date
  Links (GTM reference, Sales Enablement, Etc.)
  FAQs

## Slide 20: Example Communications Brief: Sales Kickoff Follow-up Survey
SALES KICKOFF FOLLOW-UP SURVEY |  |  | 
Objective / Description: Memo and survey link sent to SKO attendees. Survey objective is to learn SKO’s effectiveness at communicating the new FYXX GTM direction. Survey will not cover comfort with their new roles, since they will learn their new roles in the following week Prior Comms Activity: Sales Kickoff Next Comms Activity: Go Live |  |  | 
Audience: GTM SKO Attendees | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email with Survey link |  |  | 
Survey Cover Memo
Survey Outline
Closing
  Thank you for your focus at the FYXX Sales Kickoff.
  We need your feedback to identify any gaps in what you need know about the FYXX GTM model.
  Link to survey. 3-5 minutes in length
  What is your role? Geo? (demographics)
  What sessions did you attend? (Day1, Day 2, Day 3, Breakouts, On-Demand Breakouts, None)
  Rate & comment on the sessions. (ratings, free-form text)
  Would you recommend the SKO to other GTM staff? (NPS 0-10 rating)
  Are you comfortable with the updated GTM approach to selling?
  Any additional feedback?
  Thank you for your feedback. It will be kept anonymous and used to improve [Company's] GTM organization and similar future sessions

## Slide 21: Example Communications Brief: Region LT Leaders Inform Staff
REGION LT LEADERS TO INFORM KEY STAFF |  |  | 
Objective / Description: Region Leadership team (LT) members inform key staff about GTM and Org changes coming Prior Comms Activity: SKO, Comp Plan, Go-Live Next Comms Activity: Region Org Announcement |  |  | 
Audience: Key Staff Under LT | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Call |  |  | 
Key Changes to GTM Org
Details
Next Steps
  Thank you for your focus at the FYXX Sales Kickoff
  We want to make you aware of key changes affecting your team/org that will be rolled out starting on XX Date
  Outline key GTM guiding principles shared at SKO.
  Connect individual-level priorities (& comp plan) to company-level guiding principles.
  FAQs including contacts if questions or concerns about information in GTM systems
  Reach out to their manager if any questions or concerns arise.
  Your manager will provide additional info for you to communicate with your teams

## Slide 22: Example Communications Brief: Manager Post 1:1 Messaging
MANAGER POST-1:1 EMAIL (TO EMPLOYEES) |  |  | 
Objective / Description: Provide employee capstone information to reinforce FYXX GTM transformation concepts covered at SKO; comp plan design; and Go Live Prior Comms Activity: SKO, Comp Plan, Go-Live Next Comms Activity: Start messaging to partners and customers |  |  | 
Audience: GTM Employees | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email |  |  | 
We are officially working in the FY23 GTM model
Details
Next Steps
  “We are now live on FYXX GTM! Get to know your teammates. Ask your managers any questions about our FYXX GTM operating model”
  Outline key GTM guiding principles shared at SKO.
  Connect individual-level priorities (& comp plan) to company-level guiding principles.
  FAQs including contacts if questions or concerns about information in GTM systems.
  Employee should contact their manager if any questions or concerns.
  Employee should review recent history and discussions with partners (if relevant) and customers.
  Your manager will provide additional info for you to communicate with partners and customers.

## Slide 23: Example Communications Brief: Partner Messaging
PARTNER MESSAGING |  |  | 
Objective / Description: Provide PAMs messaging and script outline to use with their partner contacts. It is an opportunity to align with partners on TD’s updated GTM approach and learn about any changes to partner operations Prior Comms Activity: Manager Launch 1:1 discussion and email Next Comms Activity: GTM Leader Roadshows |  |  | 
Audience: Partners | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email. Meeting. Post to [Company] web portal for partners |  |  | 
Introduction
Messaging for each partner type
Agree next steps, closing
  [Company's] GTM approach has changed. Key priorities (more focus on cloud, new customers)
  Outline key details that impact all partner types.
  Have your GTM or offerings changed? If so, how? How do we work together during XX Year?
  CSPs: Streamlining cloud onboarding and migration. Here’s what is changing.
  SICs: Continue to focus on providing value to the customer. Communicate recent enhancements to cloud capabilities.
  ISVs: (Messaging specific to each SW vendor)
  Resellers & Distributors: Provide details on updated onboarding and cloud migration processes.
  Request follow-up meetings (if necessary) to align working relationships further.
  [Company] contact info. Link to partner portal.

## Slide 24: Example Communications Brief: Customer Messaging
CUSTOMER MESSAGING (EXISTING) |  |  | 
Objective / Description: Provide existing customers an executive-level announcement on Company's increased focus on cloud and enhanced cloud capabilities to drive increased business value (industry/solution examples). Include any other relevant GTM messaging including key contact(s) Prior Comms Activity: Manager Launch 1:1 discussion and email Next Comms Activity: GTM Leader Roadshows |  |  | 
Audience: Existing Customers | Content Developer: R | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email. Meeting. Post to Teradata web portal for partners |  |  | 
Introduction
Messaging for each customer type
Agree next steps, closing
  [Company's] GTM approach has changed. Key priorities include more focus on cloud and enhanced capabilities.
  Outline key details common to all customer industry/solution types.
  Have your needs changed? If so, how? How do we work together during XX Year?
  Industry-specific messaging.
  Solution-specific messaging.
  Request meeting with customer to share [Company's] new direction and learn customer’s 2023 needs & priorities.
  [Company] contact info (Customer AE and CSM).

## Slide 25: Example Communications Brief: GTM Leader Roadshows (Invitation)
CUSTOMER MESSAGING (EXISTING) |  |  | 
Objective / Description: Invite all GTM staff to GTM Leader Roadshows. Drive momentum, energy, and invitee’s active engagement in GTM model development. Include agenda, esp. opportunity for Q&A with GTM leader Prior Comms Activity: Full GTM Launch Next Comms Activity: Business-as-usual GTM operation and communications; surveys |  |  | 
Audience: All GTM Roles | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email/Teams/Blog/Intranet |  |  | 
Introduction
Messaging for each customer type
Agree next steps, closing
  We are now fully launched on our updated GTM model. Own your role.
  You are invited to join a session with your GTM leader to learn key priorities, activities and for Q&A
  Recall key priorities; provide additional refinement and messaging on priority-related activities.
  Collaboration needed to build and interlock updated sales roles on opportunity teams. (example)
  Introduce weekly scrum.
  Q&A
  Button to add session to calendar.

## Slide 26: Example Communications Brief: Post-GTM Launch Survey (Bi-weekly)
POST-GTM LAUNCH SURVEY (BI-WEEKLY) |  |  | 
Objective / Description: Biweekly survey to capture feedback after the GTM launch. Memo and survey link sent to all GTM staff. Survey objective is to learn staff feedback, comfort, readiness to sell in the new GTM model Prior Comms Activity: GTM Leader Roadshows, Systems Launch Next Comms Activity: Geo All-Hands Meeting (ongoing) |  |  | 
Audience: All GTM Staff | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email with survey link |  |  | 
Survey Cover Memo
Survey Outline
Closing
  We need your feedback regarding the FYXX GTM model and your role in the model.
  This is your opportunity to provide anonymous/private feedback on GTM, your role, current sales opportunity team, etc.
  Link to survey. 3-5 minutes in length
  What is your role? Geo? (demographics)
  How would you rate the FYXX GTM model? Why do you give it this rating?
  Is your role clear? If not, what needs to be clarified?
  Are you performing activities outside your role? If yes, what activities are you performing and why?
  What would you change to improve your role and the operation of your sales opportunity team?
  Any additional feedback?
  Thank you for your feedback. It will be kept anonymous and used to improve Teradata’s GTM organization.

## Slide 27: Example Communications Brief: Daily Scrum Guidance
GUIDANCE ON HOW TO RUN A DAILY TEAM SCRUM |  |  | 
Objective / Description: Set expectations and provide guidance and frameworks for how to run a daily scrum Prior Comms Activity: Post-GTM Launch Survey Next Comms Activity: None |  |  | 
Audience: All GTM Managers | Content Developer: | Delivered By: | Delivery Date:
Key Messages |  |  | 
 |  |  | GUIDING PRINCIPLES Accelerate new logo acquisition​ Boost Customer Retention & Mitigate Churn​ Deepen & Broaden Cloud Capabilities​ Scale & Activate the Partner Ecosystem​ Drive Consistent Migrations & Business Value Selling​ Improve Productivity​
Type(s): Email with links to FAQs, tutorials, and additional guidance |  |  | 
Define and highlight benefits of Daily Scrums
How to run your best Daily Scrum
Common issues / risks with Daily Scrums
  3 main functions: status or progress updates, what will be accomplished today, any current issues / barriers
  Benefits: Improvement of comms, elimination of other meetings, helps identify impediments to develop removal, highlight and promote quick decision-making, and improve the team’s level of knowledge
  Link to survey. 3-5 minutes in length
  Customize time limits
  Prepare ahead of time and take notes each scrum session
  Scrums are too long
  Discussion are unfocused
  You’re not working through current issues / barriers

## Slide 28: “Office Hours” can be set up during Launch Week to provide an additional forum where employees can go for answers
GTM Launch “Office Hours”
“Office Hours” will be an open meeting/ video bridge for GTM sellers to dial in with questions following SKO and during GTM Launch week
There will also be an accompanying [Teams/Slack/etc.] channel with information and chat
WHAT?
Provide forum for GTM employees to ask questions and obtain quick answers related to GTM Launch week questions (comp plans, IT information sources, escalations of potential issues, etc.)
WHY?
To be held from XX Date to XX Date
1 hour per day per region (APJ afternoon/EMEA morning, EMEA morning, AMS afternoon)
WHEN?
GTM information experts: [insert names here]
WHO?
Provide expert team with information sources (Leader guide, Flip Book, FAQs, contact lists for relevant IT systems, comp plans, talking points for strategic rationale)
Availability and details of “Office Hours” to be communicated post SKO and in CRO and Regional EVPs Launch Week emails
HOW?

## Slide 29
Schedule a session with your advisor
SBI Advisors help clients with practical advice, whether strategic or surgically tactical, to drive revenue and growth.
Contact your advisor to schedule a work session and tune this guidance to your situation.
Login to SBI Pro:
https://pro.sbigrowth.com/
For more resources like this, contact your advisor or visit SBI Pro.